## Sheet1
Gantt Chart | 2016-10-01 | [14 empty] | 2016-11-01 | [29 empty] | 2016-12-01
| 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Project Preparation
Project idea brainstorming
Swing checkers research/mockups
Client-Side Game Functionality
Initial board interface
Checkers rules logic
Piece movement
Board redrawing
Server-Side Game Functionality
Server/client communication research
Server/client communication programming
Server/client protocol building
Interfacing with game
Project Four Additions
Whose turn is it?
Adding King Pieces
Add Skip term button
Win conditions
Various small updates
Beginning and end screens
Bug Fixing