## Sheet1
Gantt Chart | 2016-10-01 | [14 empty] | 2016-11-01 | [29 empty] | 2016-12-01
| 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Project Preparation
Project idea brainstorming
Swing checkers research/mockups
Client-Side Game Functionality
Initial board interface
Checkers rules logic
Piece movement
Board redrawing
Server-Side Game Functionality
Server/client communication research
Server/client communication programming
Project Four Additions
Adding King Pieces
Add Skip term button
Drag & Drop pieces
Add win screen
Turn Timeout
Saving user statistics
Bug Fixing